## Slide 1
Corporate Performance Report
Quarter 2: July – September 2023-24
Performance and Business Intelligence,
Corporate Team
Policy Unit

## Slide 2: Contents
The Essex Story
    Purpose of the report
    Key points for consideration
    Actions from last quarter
    Financial Well-being
  Operating Context
    Operating context for Everyone’s Essex
    Society
    Risk: Inflation
    Essex: Reputation Tracker
    Essex: Satisfaction Tracker
    Essex: Issues Tracker
  Strategic Priorities
    Climate
    Equalities
    100 Deliverables
  Spotlight
    OFLOG
    Highways
    Performance reporting updates
  Strategic Indicators
    Everyone’s Essex: Achievements
    Measures to watch
    Performance Report Annex
    OFLOG Measures: Annex

## Slide 3
The Essex Story: Purpose of this report
Sign off the report for:
Onward transmission to PLT and the Scrutiny Committee;
Identification of any issues that require particular handling with PLT or Scrutiny Committee ahead of those discussions, or with the media/public.
Review progress
Check that agreed CLT/PLT performance actions have been completed;
Consider whether this provides CLT with assurance that actions are feeding through into delivery and therefore improved performance.
Agree an appropriate response to those issues. This might include:
Seeking assurance as a leadership team that appropriate remedial action is being taken to address performance risks;
Noting actions being taken where these are sufficient to provide assurance;
Confirming advice to PLT/Members in cases where CLT considers that remedial action is unlikely to correct deviations in performance to meet published targets within the time or resources available.
To agree organisational performance issues – including those that are:
Council agreed Everyone’s Essex targets that are at risk;
Challenges to the financial well-being of the Council;
Wider issues relating to the council’s performance;
Contextual factors that have the potential to impact on demand and budget;
Operational issues within a function won’t generally be flagged as requiring CLT discussion unless there is a need to escalate above FLT/Portfolio consideration.

## Slide 4
For this quarter, we draw attention to the measures included in the OFLOG measures, highlighting the measures which have been in place since July 2023 and drawing attention to the new areas of focus currently in consultation, and the future areas for performance reporting.
Detail outlined on slides 15 – 17 ECC performance and benchmarking in the annex (slide 41)
The Essex Story: Key Points
In this quarter, the report identifies key areas of ECC performance that are below target (strategically or functionally) and represent a risk to the Council. CLT is asked to consider:
What is driving the performance in these areas
What are the wider implications of current levels of performance in this area: financially, reputationally, politically
What are the actions we are looking to pursue organisationally to improve the position
What support is required from other parts of the organisation to address the issues
What level of assurance can we provide to PLT/Members about our ability to remediate or address the position in a reasonable timeframe
For this quarter, a special ‘spotlight’ on Essex Highways, which has a high profile locally. A recent 'Jeans and jumper' day looked at some of the surrounding issues.
A summary of recent Essex Highways data and insights, focusing on some of the challenges the network faces, including key benchmarking information against other county councils.
Detail outlined on slides 18-24
Highways
OFLOG
Spotlight for Quarter 2
As part of refreshing our approach to performance reporting, we are continuing to explore options for improving the quality of the insight that senior leaders are able to access.
Progress against the IMPOWER recommendations are outlined on slides 28-30
Performance Reporting Update

## Slide 5
The Essex Story: Actions from last quarter
Actions from Quarter 1 | Updates
Suzanne Barcz to work with each Executive Director in advance, with a further session with CLT on Performance Reporting. | Ongoing Suzanne Barcz and Performance and Business Intelligence Partners have been working with Executive Directors over the last couple of months to gather views on what could support better performance conversations; both in terms of content (ensuring that the ‘golden thread’ is maintained) and approach. There have been some proposals for ‘change control’ these will be brought through where the measures are no longer functional priorities.
Suzanne Barcz/Lucy Wightman to meet and discuss outside of this meeting | Complete Suzanne Barcz and Lucy Wightman met at the end of October to consider options for future reporting and approaches.
Agreed the proposed description of the purpose of CLT performance discussions (IMPOWER recommendation). | Complete
CLT will let Suzanne Barcz/Richard Puleston have any more comments. Report will be refined and brought back to CLT | Complete Q2 Report to CLT 28th November.
Proposed list of indicators – further work to be done. Will take forward conversation with Nicole Wood/Adrian Osbourne/Stephanie Mitchener and bring this back an ensure it links with Transformation. | Ongoing Discussion scheduled for 29/11
Key issues: CLT agreed that the GHG and People waiting measures should be the areas of focus of the PLT and scrutiny discussions. SB to link with Mark Ash/Chris Martin/Nick Presmeg to ensure the framing is right in terms of the report going to JLT and PLT. | Complete Confirmation secured prior to distribution to PLT in October
Agreed the onward transmission of the Q1 report to PLT and Scrutiny Committee | Complete Circulated to PLT, and Scrutiny discussion completed on 7th November
Updates on the IMPOWER and Equalities work – fuller articulation to be brought to CLT | Update included, but substantive update requested
An action log was created for the Quarter 1: Corporate Performance Report. Updates to those actions are listed below, noting most are complete or progressing.
Complete | Scheduled/in development

## Slide 6
The Essex Story:
Financial Well-being, Developing a future framework
Following the performance reporting work undertaken by IMPOWER, over the coming weeks, CLT will be considering options for a small suite of ‘ambition’ targets that look to give ECC a number of measures with opportunities for cross-council working, that link closely with the business plan, financial sustainability and resident priorities. Below is an initial list considered with finance*. All [targets] and [timescales] are illustrative.
Support [20%] more children with EHCPs in mainstream schools [by 2028]
Reduce energy use in ECC building by [20%] [by 2027]
Reduce residual waste by [15%] [by 2026]
Increase reablement where no ECC support required to [60%] [by 2025]
Reduce the proportion of spot-purchased Domiciliary Care by [20%] [by 2025]
Maintain the balance of support for children, young people and families
Continue to reduce people supported in residential settings by [5%] per year
Reduce ECC mileage by [20%] [by 2026]
Reduce urgent repairs to highways
Reduce the demand for home to school transport by [10%] [by 2028]
Reduce the proportion of CIC supported in residential settings
*noted that a gap in these proposals is on the economy, where discussions noted that there needs to be a measure identified where ECC can take direct action to affect an outcome, and that outcome be linked with ECC sustainability

## Slide 7
Inflation remained at 6.7% in September. (For November, inflation is now at 4.6% against the Bank of England's target of 2%).
High inflation rates also reflect rising living costs for residents – we project that by July 2024, some 43,000+ households in Essex may have incomes below the level necessary to pay for food and essential bills. This creates considerable risk around future demand pressures and considerable uncertainty around future council tax and business rate revenues.
The Bank of England left interest rates unchanged at 5.25% (next update 14th December), after 14 consecutive increases. This continues to drive up the cost of borrowing with direct implications for the cost of financing ECC’s capital programme.
THE ECONOMY
Health & wellbeing
Children & families
Levelling up
Operating Context: Everyone’s Essex
A priority focus for the Levelling Up work continues to be mobilising delivery for the 4 Levelling Up Essex cohorts. The Levelling Up cohorts cover all districts in Essex and interventions will therefore include non-Levelling Up districts and boroughs.
Following on from the plans developed for young people not in employment, education of training (NEET's) and Working Families, the focus is now on people with a learning disability, mental health need and children on free school meals, with a view to delivery plans for all cohorts being agreed by early 2024.
The large-scale community engagement project in Rural Braintree, and '100 days 100 families' project in Canvey Island are both shortly due to conclude, both of which have focused on identifying and learning what levelling up means for communities and families. This work will inform the ongoing development of the LU agenda in both places.
While the number of children in care has remained relatively stable during the last quarter, the number of children on a child protection plans continues to rise, increasing from 677 to 772 in the last 9 months, although Essex continues to benchmark well.
While the number of Child Protection Plans are increasing, overall, the number of open cases has seen a slight decline, the result of a reduction in the number of children on a Child in Need Plan.
Attainment outcomes across all key stages within the primary phase increased in 2023 and continue to compare favourably with national averages. In addition, the span between the highest and lowest performing districts across Essex was lower than in 2022. Whilst many Levelling Up initiatives are still in their infancy, this bodes well for future years. The secondary phase key stages saw the anticipated reduction in performance as marking thresholds reverted to those used in 2019 (2022 made some allowances for post-pandemic effects). Reductions were also seen nationally but Essex performance continues to be lower than national averages in most KS4 measures. The performance of disadvantaged pupils remains a concern with those in Essex performing lower than their national peers across all age ranges.
Whilst the Essex health system remains under pressure, progress has been made on the length of time people wait for an intervention from Adult Social Care. Since 31st March 2023, the number of adults awaiting Care Act assessment has dropped from 2,274 to 1,908 (16%).
A review was undertaken on how cases are prioritised and to ensure those with the highest priority get an appropriate response.
The 12 identified initiatives to address the overall number of people waiting are being progressed and ASC continue to look at all areas of prevention to reduce demand and promote independence.
Care Technology continues to prevent, reduce and delay demand coming into ASC and support the independence of over 8,000 adults across Essex.
Notes: Inflation was 6.7% for Q2, updated to 4.6% for November forecast to continue to reduce this year. Interest rates remain unchanged from Q1 at 5.25%

## Slide 8
Operating Context: Society
Crime and feeling safe
Employment
Over a third of crime in Essex is categorised as Violent Crime, which is down 7.8% compared to the same period last year.
Unemployment rates have fallen to pre-coronavirus pandemic levels, following a rise during the pandemic.
Chart: 
| Achieved | Not Achieved
segments | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Values | 0.614 | 0.386
61.4%
In September 2023, around 6 in 10 adults in Great Britain said they tend to be satisfied with the police in the UK.
Chart: Essex Total Crime down 8.2% since last year
| Q1 Jun-20 | Q2 Sep-20 | Q3 Dec-20 | Q4 Mar-21 | Q1 Jun-21 | Q2 Sep-21 | Q3 Dec-21 | Q4 Mar-22 | Q1 Jun-22 | Q2 Sep-22 | Q3 Dec-22 | Q4 Mar-23 | Q1 Jun-23 | Q2 Sept-23
Essex Total Crime | 18207 | 17690 | 15968 | 18065 | 18206 | 16609 | 14815 | 17099 | 16121 | 15402 | 13139 | 14896 | 14510 | 14138
Essex Violent Crime | 6209 | 6375 | 5423 | 6153 | 7000 | 6997 | 6352 | 6930 | 6472 | 6092 | 5430 | 6130 | 5623 | 5614
Chart: Employment rate (16-64), down 0.2% from Q4 2022/23
| Q1 2021 | Q2 2021 | Q3 2021 | Q4 2021 | Q1 2022 | Q2 2022 | Q3 2022 | Q4 2022 | Q1 2023 | Q2 2023
Essex | 75.6 | 76 | 76.2 | 78.3 | 79.2 | 79 | 79 | 77.9 | 77.6 | 77.3
UK | 75.1 | 75.4 | 75.4 | 75.6 | 75.4 | 75.5 | 75.7 | 76 | 75.9 | 75.6
Crime and fear of crime is a contributing factor to people’s satisfaction with place, and with their own wellbeing.
Economic factors could have a negative impact on crime
Chart: Claimant rate 16+ remains stable at 2.8%
| 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200
Essex (%) | 2.8 | 2.7 | 2.8 | 2.7 | 2.7 | 2.8 | 2.8 | 2.9 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8
Great Britain (%) | 3.6 | 3.5 | 3.6 | 3.6 | 3.6 | 3.6 | 3.7 | 3.8 | 3.6 | 3.7 | 3.7 | 3.6 | 3.6 | 3.7
Essex continues to perform strongly in employment performance compared with the national picture. High employment rates will contribute to reduced demand and enhance council tax yield. However, the impact of the cost of living will still impact in-work families
Breakdown:
Number of people unemployed by Age Group:
4.7K
aged between 16-24
15.3K
aged between 25-49
5.9K
aged 50+
Notes: Crime and feeling safe:
https://www.ons.gov.uk/peoplepopulationandcommunity/wellbeing/articles/ukmeasuresofnationalwellbeing/dashboard
Participation & satisfaction:
https://www.ons.gov.uk/peoplepopulationandcommunity/wellbeing/articles/ukmeasuresofnationalwellbeing/dashboard
Participation in, satisfaction with, and balance between work and leisure activities represent people’s lifestyle choices. Measures in this domain cover subjective and objective measures related to work, leisure and volunteering.
Employment rate 16-64: is down 1.1 % from last quarter (Nomis) Economically Active
https://www.ons.gov.uk/employmentandlabourmarket/peopleinwork/employmentandemployeetypes/timeseries/lf24/lms
Claimant rate 16+ up 0.2% from last quarter (Nomis) Claimant Count

## Slide 9
ECC Strategic Risk (SRR0092): Inflation
Inflation has reduced since its peak in October 2022 at 11.1%, now currently at 4.6% for November (against the Bank of England’s target of 2%).
High inflation rates drive increasing costs for ECC and have increased pressure on ECC capital and revenue budgets and creates considerable risk around future demand pressures.
The Bank of England raised interest rates on fourteen consecutive occasions, with the base rate remaining at 5.25% since August, driving up the cost of borrowing.
We continue to monitor inflation pressures monthly; regular updates and potential impacts are reported to CLT and PLT.
Rent & Mortgage risk in Essex
The average UK house price was £291,000 in September 2023.
Around 35% of adults in Great Britain paying rent or mortgage said they were finding the payments very or somewhat difficult to afford*
40% said their payments had increased in the last six months*
The proportion of mortgage payments made by Direct Debit which failed because of insufficient funds last month was the highest since May 2023.
Chart: Inflation was 6.7% for Q2, updated to 4.6% for November forecast to continue to reduce this year. Interest rates remain unchanged from Q1 at 5.25%
| 2020 Q1 | 2020 Q2 | 2020 Q3 | 2020 Q4 | 2021 Q1 | 2021 Q2 | 2021 Q3 | 2021 Q4 | 2022 Q1 | 2022 Q2 | 2022 Q3 | 2022 Q4 | 2023 Q1 | 2023 Q2 | 2023 Q3 | 2023 Q4 | 2024 Q1
Inflation | 1.6671 | 0.61667 | 0.59667 | 0.53353 | 0.60958 | 2.0519 | 2.7716 | 4.9074 | 6.2195 | 9.1692 | 10.0221 | 10.7 | 7.9 | 6.7 | 4.6
Forecast | 10.0221 | 10.7 | 9.65 | 6.89 | 5.4 | 2.9 | 1.5
Interest rate | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.25 | 0.75 | 1.25 | 2.25 | 3.5 | 4.25 | 5.25 | 5.25 | 5.25
8
(4, 2)
12
(4, 3)
Impact
Probability
Strategic Risk
Essex House prices falling by 0.7% in September compared to the same period last year
Average monthly rents across the UK continue to rise in October, taking monthly rents to a new record high.
The average rental value for new tenancies in the East of England is £1,216 per calendar month
Rents in the East of England increased by 9.7% compared to same period last year (Oct 22 –Oct 23)
Affordability: In the last year, affordability has weakened the most in London, the East of England and Scotland.
Regional Rent: ↑ 9.7%
Average % tenant income spent on rent: 34.2%
Regional insight
Predominant age group:
20–29
Median tenant gross income* £30,000
Predominant rental band: £750–£1k
National insight
Current risk score
Target score
Operating Context: Essex Risk
Notes: *according to those asked in October 2023
Rent and Mortgage insight:
Source: https://www.ons.gov.uk/economy/inflationandpriceindices/articles/costoflivinginsights/housing
Source: https://homelet.co.uk/-/media/project/barbon/homelet/homelet-documents/homelet-rental-index/2023-21-september-homelet_dataloft_rental-report_300.pdf

## Slide 10: Operating Context: Essex Reputation Tracker
Levelling Up Progress Q3
Latest data (Oct ’23)
Data on the below charts are gathered from the ECC Residents panel, residents were asked:
‘To what extent do you think these statements apply to ECC’
ECC compared to National benchmark
Data gathered from ECC Residents panel. We asked “Here are some things that other people have said about their council. To what extent do you think these statements apply to Essex County Council? The analysis excludes ‘don’t know’ responses. Reported figures include respondents who agreed ‘to some extent’ or ‘a great deal.’ The base sizes for Oct ‘23 were as follows: . Treats all people with respect n = 440; Is trustworthy n = 482; Provides good customer service n = 456; Is making the local area a better place to live n = 518; Provides good value n = 503; Acts on the concerns of residents n = 510; Listens to the concerns of its residents n = 509. Is efficient and well-run n = 504. The national benchmark comparison was obtained from the Yonder Omnibus survey Sept 2023, asking similar questions about respondents view of their local areas and councils. n=~1,815
Trend
Chart: 
| Jan '22 | Apr '22 | Jul '22 | Oct '23 | Apr '23 | Oct '23
Listens to residents’ concerns | 0.5 | 0.39 | 0.43 | 0.41241 | 0.36947 | 0.39571
Acts on residents’ concerns | 0.51 | 0.34 | 0.42 | 0.36858 | 0.36465 | 0.35799
Provides good value | 0.53 | 0.46 | 0.47 | 0.497 | 0.38184 | 0.43976
Making the local area a better place to live | 0.54 | 0.46 | 0.44 | 0.43556 | 0.38372 | 0.37486
Provides good Customer service | 0.61 | 0.54 | 0.52 | 0.56345 | 0.53364 | 0.53323
Trustworthy | 0.62 | 0.51 | 0.59 | 0.56082 | 0.55284 | 0.52551
Treats all with respect | 0.71 | 0.71 | 0.72 | 0.68561 | 0.71977 | 0.7071
Efficient & well run | 0.47 | 0.41 | 0.45 | 0.4378 | 0.36224 | 0.44106
Chart: 
| #N/A | #N/A | #N/A | -3.999999999999998E-2 | #N/A | -1.0000000000000009E-2 | #N/A | #N/A
Worse | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1
National Benchmark | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1
Better | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1
Treats all people with respect
Is trustworthy
Provides good customer service
Is making the local area a better place to live
Provides good value for money
Acts on residents' concerns
Listens to residents' concerns
Is efficient and well run
Notes: FROM ALASTAIR: mock-up of the indicator-based section of the LU programme report – want to ensure consistency
Will need to select highlights from the longer report – 12 missions, ~9 slides
Highlight those with updates to data / change in performance
Combine benchmarking and change to one page??
Purpose: Tracking / Trend

## Slide 11: Operating Context: Essex Satisfaction Tracker
Satisfaction tracker Q3
Chart: 
| Jan '22 | Apr '22 | Aug '22 | Oct '22 | Apr '23 | Oct '23
Essex County Council | -31 | -51 | -47 | -48 | -57 | -47
Environment, nature & climate crises
Rise in cost of living
Tackling inequalities
National benchmark (for local councils) | -8 | -8 | -8 | -8 | -8 | -20
Satisfaction with ECC meeting community need
NET SCORE: % satisfied minus % dissatisfied
Chart: 
| Environment, nature & climate crises | Rise in cost of living | Tackling inequalities
Oct '22 | 0.14 | 0.1 | 0.09
Apr '23 | 0.19 | 0.13 | 0.19
Oct '23 | 0.19 | 0.15 | 0.21
Satisfaction with ECC’s response to...
% satisfied
-33
-35
-10
NET SCORE:
Chart: 
| Environment, nature & climate crises | Rise in cost of living | Tackling inequalities
Oct '22 | 0.29 | 0.14 | 0.27
Apr '23 | 0.3 | 0.13 | 0.34
Oct '23 | 0.31 | 0.16 | 0.34
Confidence that ECC can support the response to…
% very / fairly confident
Chart: 
| Environment, nature & climate crises | Rise in cost of living | Tackling inequalities
Oct '22 | 0.32 | 0.22 | 0.19
Apr '23 | 0.42 | 0.31 | 0.33
Oct '23 | 0.38 | 0.27 | 0.26
% Feel informed about ECC’s response to…
% very / fairly informed
Latest data: October 2023
Data gathered from ECC Residents panel. We asked ‘How satisfied or dissatisfied are you with Essex County Council’s local response to…?’; ‘Do you feel confident that Essex County Council can support the effort towards…?’, ‘Before today, how informed would you say you were about the work Essex County Council is doing to tackle…?’, ‘Are you satisfied or dissatisfied with the way Essex County Council is doing its job of meeting the needs of Essex people, businesses, and communities today?’ All respondents Oct’ 22, n = 504; Apr ‘23 n=489; Oct ‘23 m=542 ‘Don’t know’ responses are not shown but included in the base size.
Data on the below charts are gathered from the ECC Residents panel, residents were asked:
‘How satisfied or dissatisfied are you with Essex County Council’s local response to…?’

## Slide 12: Operating Context: Essex Issues Tracker
Comparison to Previous Position
Chart: 
| 0.43 | 0.23 | 0.17 | 0.17 | 0.15 | 0.18 | 0.1 | 0.15 | 0.12 | 0.14000000000000001 | 0.16 | 0.12
Previous Datapoint | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1
Latest Datapoint | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1
National Health Service / Hospitals / Healthcare
Inflation/prices
Housing
Lack of faith in politics / politicians / local government
Crime/Community safety
Pollution / Environment / climate change
Population levels/over-population
Economy/economic situation
Poverty / inequality
Immigration / immigrants
Social Care provision
Education/Schools
Issues tracker Q3
Previous quarter/ datapoint
Latest quarter/ datapoint
Data gathered from Essex Residents Pulse survey April 2023 and October 2023. We asked ‘What would you say are the most important issues facing Essex today? Respondents could select up to 3 responses. Base sizes: all respondents who answers in April 2023 = 489; October 2023 = 542 Chart shows top 12 responses
Latest data: October 2023
Essex Issues Tracker data is gathered from the ECC Residents panel, we asked residents:
‘What would you say are the most important issues facing Essex today?’
Notes: FROM ALASTAIR: mock-up of the indicator-based section of the LU programme report – want to ensure consistency
Will need to select highlights from the longer report – 12 missions, ~9 slides
Highlight those with updates to data / change in performance
Combine benchmarking and change to one page??
Purpose: Tracking / Trend

## Slide 13
Chart: Essex GHG emissions MtCO2e
| 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
Projection | 8.22 | 8.22 | 7.94 | 7.69 | 7.52 | 7.34 | 7.12 | 6.72 | 6.34 | 6.02 | 5.67 | 5.32 | 4.97 | 4.7 | 4.43 | 4.09 | 3.83 | 3.45 | 3.15 | 2.87 | 2.59 | 2.34 | 1.92 | 1.75 | 1.61 | 1.46 | 1.31 | 1.17 | 1.07 | 0.98 | 0.91 | 0.84 | 0.81
Actual | 8.22 | 8.42 | 8.09
Strategic Priorities: Climate
243,373
Trees planted by Essex Forest Initiative since 2020.
New woodland contributes to delivering net zero carbon, nature recovery, reduces flooding, cooling city centres and provides protection against airborne pollution
61.7 Hectares
Planted (from 2021/22 – 22/23)
13.8km
Hedgerows planted
(2022/23)
Percentage of land that is now green infrastructure
Energy Efficiency – Net Zero Policy
14%
30%
2040 target
A
ECC rating for Carbon Disclosure Project
39%
(Q2) Total consumption Solar Energy Produced by ECC Sites Fed to Grid (Wh)
Year | Domestic Actual | Projections | I&C Actual | Projections | Industrial Actual | Projections | Transport Actual | Projections | Waste Actuals | Projections
2018 | 2.16 | 2.16 | 1.51 | 1.51 | 0.35 | 0.35 | 3.07 | 3.07 | 0.97 | 0.97
2019 | 2.17 | 2.09 | 1.54 | 1.41 | 0.36 | 0.33 | 3.25 | 2.98 | 0.89 | 0.89
457.8M
(Q2) Total Solar Energy Produced by ECC Sites (Wh)
A turnaround on Energy Efficiency Standards for landlords could lead to costs of up to £325 per year for tenants on elevated energy costs
WWF Science based target 3.19 MtCO2e by 2030
Heat pump installation is behind the curve with an estimated 13,000 qualified engineers needed in Essex to carry out installations and maintenance to meet Net Zero outcomes
8.09 MtCO2e
Actual (2020)
0.81 MtCO2e
Projection 2050
Notes: Trees/hectares: planting season starts in November, so no changes from Q1.

## Slide 14
ECIAs by function |  |  |  | 
Function | 2022/23 | 2022/23 | 2023/24 | 
 | # | % | # | %
Adult Social Care | 55 | 21% | 20 | 22%
Chief Executive | 7 | 3% | 4 | 4%
Children, families & education | 43 | 16% | 16 | 17%
Climate, Environment & customer services | 61 | 23% | 24 | 26%
Corporate Services | 36 | 13% | 5 | 5%
Economy, Investment & Public Health | 56 | 21% | 18 | 20%
Organisation Development & People | 10 | 4% | 5 | 5%
Total | 268 |  | 92 | 
Workforce representation:
Strategic Priorities: Equalities
Chart: 
| Female employees | Male employees
Senior roles | 0.55 | 0.45
Workforce | 0.731 | 0.269
Everyone’s Essex places great emphasis on addressing inequalities and improving life chances of our most vulnerable. We are building on our Year 1 equality objectives progress review report which we published in June this year.
We are now developing and delivering an equalities insight plan that will deepen our understanding of communities across Essex and improve both the quality and coverage of the data we hold on those who use our services. We have drawn together a multi-disciplinary team to:
better understand, for each ECC function, the data that is collected by ECC and in commissioned services, and to improve the information we collect;
analyse available data to understand if groups experience differential impacts in terms of access to services or outcomes;
assess the relationship between particular protected characteristics and key outcomes across the Essex population, irrespective of whether individuals are in touch with ECC services; and
explore what further insights are needed to better understand the lived experience of different populations and groups within Essex, including of accessing and using public services.
EDI training by function
Measure​ | Target​ | Q3 (22/23)​ | Q4 (22/23)​ | Q1 (22/23)​ | Q2 (22/23)​ | Direction of Travel​
 |  | Dec 22​ | Mar 23​ | Jun 23​ | Aug 23​ | 
% of employees who have completed the Equality and Diversity e-learning modules​ | 75-80%​ | 79.6%​ | 83.3%​ | 82.1%​ | 82.7% | ↑
Adult Social Care​ | 75-80%​ | 85.9%​ | 88.0%​ | 88.3%​ | 89.1% | ↑
Chief Executive's Office​ | 75-80%​ | 94.8%​ | 93.7%​ | 94.3%​ | 92.6% | ↓
Children & Families​ | 75-80%​ | 75.9%​ | 84.2%​ | 84.3%​ | 83.7% | ↑
Corporate Services​ | 75-80%​ | 97.4%​ | 97.4%​ | 96.9%​ | 97.1% | ↑
Education​ | 75-80%​ | 56.1%​ | 56.7%​ | 59.4%​ | 60.2% | ↑
People and Transformation​ | 75-80%​ | 94.8%​ | 94.9%​ | 95.4%​ | 96% | ↑
Climate, Environment & Customer Services​ | 75-80%​ | 70.1%​ | 76.6%​ | 69.5%​ | 70.6% | ↑
Economy, Investment & Public Health​ | 75-80%​ | 89.1%​ | 91.7%​ | 92.7%​ | 93.7% | ↑
EMBEDDING EQUALITIES
ORGANISATIONAL HEALTH
Notes: Community: we are committed to addressing inequalities and levelling up life change for our residents and advancing equality of opportunity for our communities.
Workforce: We are committed to being an employer that values difference and attracts, recruits and retains talented individuals from a diverse range of backgrounds. We will support and encourage our employees to be the best they can be at work and provide them with an employment deal that is fair and inclusive.

## Slide 15: Strategic Priorities: 100 Deliverables
The 100 deliverables are commitments made in our annual plan for 2023/24. Reporting on progress against projects and outcomes will be included throughout the financial year
Notes: Awaiting update from Patrick and team. Due 20/11/23

## Slide 16
Spotlight: OFLOG Measures
What are the OFLOG Measures?
OFLOG confirmed the ‘launch’ metrics in July 2023, with the aim to provide accessible data, insight and analysis around the performance of local government, to be more transparent as well as to support service improvement.
OFLOG have focused on a small number of metrics, the four areas are: Waste management, Adult Social Care, Adult skills and Finance.
These selected metrics have been made available on a new online tool, which will bring together a selection of existing measures across a subset of service areas, for data that is available at different levels of local authority, from Mayoral Combined Authority to District Council level.
OFLOG will periodically review the metrics under each service area and will continue to engage with local authorities.
Further service areas will be added to the OFLOG list, as well as existing service areas being expanded, as the metrics are developed and improved.
Local authorities are invited to provide feedback on their experience and the ease of use of the new online tool.
Waste Management
Adult Social Care
Adult Skills
Finance
More information can be found here
Work is underway to ensure these measures form part of future ECC performance management reporting
Household waste recycling rate (%)
Residual household waste (kg per household)
Recycling contamination rate (%)
Requests resulting in a service
Workforce turnover rate
People in adult social care, quality of life
Carers of people in adult social care, quality of life
Short-term service provision
People who use services who found it east to find information
Carers who found it easy to find information about services
19+ further education and skills achievements per 100,000 population
19+ further education and skills achievements per 100,000 population (excluding apprenticeships)
Adults with a Level 3 or above qualification
Non-ringfenced reserves as % of net revenue expenditure
Non-ringfenced reserves as % of service spend
Total core spending power per dwelling (£)
Level of Band D council tax rates (£)
Social care spend as % of core spending power
Debt servicing as % of core spending power
Total debt as % of core spending power
Initial areas with metrics delivered in July 2023:
Currently reported | In development for reporting | Not reported
ECC performance on these initial measures can be found in the OFLOG Annex

## Slide 17
Areas with metrics currently being shared for comment with local authorities:
OFLOG Measures
Business and Economic Growth
Corporate and Finance
Planning
Roads
Waste Management (fly-tipping)
Births of new enterprises [upper tier, unitary authorities, MCAs] Deaths of enterprises [upper tier, unitary authorities, MCAs] Number of high growth enterprises [upper tier, unitary authorities, MCAs]
Gross Value Added (GVA) per hour worked [upper tier, unitary authorities, MCAs] Gross median weekly pay (£) [upper tier, unitary authorities, MCAs] Employment rate for 16-64 years olds [upper tier, unitary authorities, MCAs]
Percentage of Ombudsman complaints upheld [all tiers] Number of upheld Ombudsman complaints per 10,000 population [all tiers] Council tax collection rates [lower tier, unitary authorities, London and metropolitan boroughs]
Non-domestic rates collection rates [lower tier, unitary authorities, London boroughs and metropolitan boroughs]
Currently reported | In development for reporting | Not reported | N/A
Percentage of major planning applications decided on time (district matters)
Percentage of major planning applications decided on time (County)
Percentage of non-major planning applications decided on time (district matters)
Percentage of major planning applications overturned on appeal (district matters)
Percentage of major planning applications overturned on appeal (county matters)
Percentage of non-major planning applications overturned on appeal (district)
Date when a Local Plan was formally adopted by an authority (lower tier)
Fly-tipping incidents per 1,000 people Fly-tipping fixed penalty notices issued per incident Fly-tipping fixed penalty notices issued per 1,000 people Fly-tipping fixed penalty notices percent paid Fly-tipping fixed penalty notices paid per incidents Fly-tipping enforcement actions per incident
Percentage of local authority A roads considered for maintenance [upper tier below MCAs, unitary authorities, London and metropolitan boroughs]
Percentage of local authority B and C roads considered for maintenance [upper tier below MCAs, unitary authorities, London and metropolitan boroughs]
Number of casualties in reported road traffic collisions per billion vehicle miles [upper tier below MCAs, unitary authorities, London and metropolitan boroughs]

## Slide 18
Spotlight: OFLOG Measures
Areas proposed for development next (subject to change), measures underneath each to be confirmed for each area
Childrens Social Care
Homelessness and Rough Sleeping
Youth Justice & Accommodation
Public Health
Future areas for development:
Animal Welfare
Anti-Social Behaviour
Asylum Services
Climate Change Mitigation and Adaptation
Early Years
Employment Rate
Environment
Housing
Neighbourhood Crime
Parks and Green Spaces
Public Transport
Special Educational Needs and Disabilities (SEND)
Sport, Leisure & Recreational Services (inc. Libraries)
Support Services for vulnerable people

## Slide 19
Spotlight: Highways
Essex has one of the largest and busiest road networks in the country.
The highways network is vital to keep the economy and productivity moving, as well as maintaining social growth and relations.
Our highways network also helps to address key policy areas, that are not often seen or recognised as a barrier for people, these include;
Decarbonisation: Transport emissions remain high; there is a need for better infrastructure to support the move towards an increase in electric vehicles, and other sustainable transport modes for journeys
Inequalities: The Essex road network provides access to education, skills, and jobs for all. Communities are reliant on the network, and it’s important that these are inclusive and accessible for public use and need;
Health and wellbeing: Increased active travel to help support improved health outcomes and would contribute to reduce emissions. Nationally, road safety continues to be a key area, to reduce accidents and deaths on the highways network.
Housing and communities: It’s important to ensure we help form sustainable and resilient communities with considered planning that enables sustainable, reliable and safe network including and active travel provisions;
Economic stability and growth: Effective transport infrastructure and systems are vital for a successful economy across the UK, as well as supporting links to international trade.
Target score:
9
(3, 3)
Probability
Impact
Strategic Risk: SRR0098 Tolerate
Highways Network: Due to insufficient investment, extreme weather and inflationary increases in the cost of resource and materials, there is a risk of further deterioration to the highways network. This will result in public dissatisfaction and increased number of complaints, insurance claims and
safety incidents
Current risk score:
9
(3, 3)
October Status: In-progress: Develop a long-term, sustainable investment strategy to arrest deterioration as current funding has been reduced over recent financial years.
A business case is being prepared for 2024/25, and this will be shared with Members via the budget setting process.
The new business case outlines the impacts of budgets remaining static, as well as levels of funding that may be required to slow down or prevent deterioration longer terms, for example, and extra £11m/annum targeted towards PR1 routes only would support maintaining condition on this strategic aspect of the network, over a 10-year period. For subsidence sites, an element (c.£1.5m) of the existing capital budget has been ‘ring-fenced’ for dealing with subsidence sites. However, this only reduces capital spend on other carriageway maintenance treatments
Annual Survey: Continued annual survey to monitor situation. The current level of annual capital-based budget investment in carriageways continues to be held at ECCs £35.15m. This is significantly lower than the modelled deterioration annually of £85.4m (24/25 budget business case) and will not result in improvements to condition and will now see increasing deterioration annually. Status: On-going
8.5bn miles
Total motor vehicle mileage (2021) Essex position 1/24
4,054km
Total Rural 'C' and 'U' roads (km)
Essex has one of the largest networks for heavily trafficked road classes
8,331 km
Total length of road network
472m
Miles driven by HGVs on Essex Highways (2021)
Largest road network of the 24 County Councils
Essex: 7th
Introduction: Essex Highways
Road Length: Essex ranks second place (out of all 24 county councils) for more ‘Urban’ and heavily trafficked roads, with our closest statistical neighbours in terms of road length and road class as Hampshire, Kent, Lancashire, Surrey and Hertfordshire.

## Slide 20
Spotlight: Highways
Road conditions & expenditure on roads
Percentage of network in need of repair 2021/22: REVENUE
Smallest and Largest 5-year average REVENUE £ per Km
Smallest and Largest 5-year average CAPITAL £ per Km
Percentage of network in need of repair 2021/22: CAPITAL
Herts
Essex
£2,293 per km Revenue
(Rank: 14/24)
£8,510 per km Capital (Rank: 23/24)
£4,739 per km Revenue
(Rank: 24/24)
£11,580 per km Capital
(Rank: 24/24)
Total Road length 8,331km
Total Road length 5,054km
Essex
Derbyshire
Herts
£8,510 per km Capital (Rank: 23/24)
£2,293 per km Revenue (Rank: 14/24)
£2,049 per Capital km
(Rank: 1/24)
£1,953 per km Revenue (Rank: 10/24)
£11,580 per km Capital
(Rank: 24/24)
£4,739 per km Revenue (Rank: 24/24)
Total Road length 8,331km
Total Road length 5,657km
Total Road length 5,054km
22%
33%
32%
32%
2020/21 data
Chart: 
| U Roads | B&C Roads | A Roads
Hertfordshire | 0.07 | 0.04 | 0.02
Chart: 
| U Roads | B&C Roads | A Roads
Derbyshire | 0.28 | 0.24 | 0.2
Chart: 
| U Roads | B&C Roads | A Roads
Hertfordshire | 0.07 | 0.04 | 0.02
2020/21 data
Chart: 
| U Roads | B&C Roads | A Roads
Essex | 0.11 | 0.02 | 0.03
Chart: 
| U Roads | B&C Roads | A Roads
Essex | 0.11 | 0.02 | 0.03
22%
Satisfaction with road conditions
Satisfaction with road conditions
Essex Road conditions, presented as the percentage of road network in need of repair for both Revenue and Capital budgets. This includes County Council performance ranking (24 in total). Essex continues to receive poor levels of satisfaction
Notes: Norfolk – remove
Essex scale – 40%

## Slide 21
Spotlight: Highways
Road conditions & expenditure on roads
Chart: 
| 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22
% of ECC A Roads where maintenance should be considered | 0.04 | 0.05 | 0.06 | 0.03 | 0.04 | 0.05 | 0.04 | 0.02 | 0.02 | 0.02 | 0.03 | 0.02 | 0.03 | 0.03 | 0.03
County Council Mean | 0.04 | 0.04 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.04 | 0.04 | 0.04
Chart: 
| 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22
% of ECC B & C Roads where maintenance should be considered | 0.06 | 0.07 | 0.08 | 0.07 | 0.07 | 0.07 | 0.05 | 0.04 | 0.04 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02
County County Mean | 0.08 | 0.08 | 0.09 | 0.09 | 0.1 | 0.1 | 0.08 | 0.07 | 0.05 | 0.05 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
A-roads are classed as major roads that link regional towns and cities. These are also referred to as 'trunk' roads. A-roads can be either single or dual-carriageways and are found in both rural and urban areas.
Against the County Council Mean (4%), Essex has a lower maintenance requirements on A-roads for 2021/22:
Essex 3%
Derbyshire: 20%
B & C roads are sometimes referred to as ‘minor’ roads, where they connect small towns and villages. These roads are important to communities.
Against the County Council Mean (6%), Essex has lower maintenance requirements on B & C roads:
For 2021/22:
Essex: 2%
Derbyshire: 24%
Percentage of A-roads where maintenance should be considered: ECC v County Council mean
Percentage of B & C roads where maintenance should be considered: ECC v County Council mean

## Slide 22
Chart: 
| 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Essex | 31 | 28 | 30 | 24 | 30 | 29 | 18 | 22
Leicestershire | 45 | 45 | 46 | 36 | 42 | 44 | 39 | 40
County Council average | 35.8636 | 34.3636 | 34.6522 | 27.125 | 33.875 | 32.5 | 27.5 | 30.625
Leicestershire County Council consistently rank in the top counties in terms of public satisfaction with road conditions, and other highways related topics.
Spotlight: Highways
Satisfaction
The National Highways and Transport Network:
Annual Public Satisfaction Survey:
Q. Satisfaction with condition of highways (KBI 23)
Satisfaction with the condition of Highways
Highways continues to be a highly political area, that has caused some anxiety around resident satisfaction and perception that our road network is poor. Essex continues to remain in the lower quartile in the National Highways and Transport Network: Annual Public Satisfaction Survey.
However, Essex have some of the lowest defects on our road network compared to all other counties (24), especially given our geographical size.
Resident satisfaction: insight
Essex County Council
In 2022, we saw a small upturn in levels of satisfaction, following a large decrease in 2021.
However, Essex has followed the pattern of increases and decreases of the county council average across the years, albeit always with a slightly lower value.
We understand that Essex spend per km, compared to other county councils is high.
We also understand that Essex have spent more with Ringway Jacobs than originally envisaged in the contract.
Is there an opportunity to focus on targeted communication campaigns to shift public perception of the performance on Highways?
Essex has always received comparatively low satisfaction scores in this survey, and for this indicator, even though our road condition is comparable to or better than most authorities.
Notes: Red box – bold key messages

## Slide 23
Spotlight: Highways
Road conditions & expenditure on roads
Chart: Essex Highways Commissioning 2023/24 CAPITAL Budget (£000)
| Road Maintenance | Bridges | Footway Maintenance | LED rollout | Local Highways Panels | Street Lighting Replacement | Other
 | 35150 | 9450 | 8000 | 7000 | 4800 | 3000 | 10106
Chart: Highways Maintenance REVENUE Budget 2023/24 (£000) *
| Ongoing Operator Payments for A130 PFI | Roads And Footways | Street Lighting | Winter Service | Bridges | Other
 | 19210 | 14556 | 14190 | 3450 | 1827 | 4854
* This discounts service elements/budget lines which through income or specific grants have negative values, such as Congestion and Traffic Mgt Act.
Other Revenue elements include Highways Asset Management, Park and Ride, Public Rights Of Way and Road Safety
Other Capital elements include Surface Water Alleviation, Active Travel, Safety Barrier Replacement, Traffic Signal Refurbishment, Cycle Asset Renewal and Public Rights of Way
These show the original 2023/24 Highways budgets, as published in the ECC Annual Plan
Notes: Include text from Stuart

## Slide 24
Spotlight: Highways
Challenges
The two graphs below outline some of the challenges in maintaining Essex’s roads in the years ahead
Chart: Recent road condition and projected deterioration in % of roads where structural maintenance is needed
| 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33
PR1 | 0.02 | 0.03 | 0.03 | 0.03 | 0.03
PR2 | 0.02 | 0.03 | 0.02 | 0.02 | 0.02
Local | 0.1 | 0.11 | 0.11 | 0.11 | 0.15
PR1 Projected Estimate | 0.03 | 0.03 | 0.04 | 0.05 | 0.06 | 0.08 | 0.1 | 0.12 | 0.14 | 0.17 | 0.19
PR2 Projected Estimate | 0.02 | 0.03 | 0.03 | 0.04 | 0.06 | 0.07 | 0.09 | 0.1 | 0.12 | 0.13 | 0.15
Local Projected Estimate | 0.15 | 0.17 | 0.18 | 0.21 | 0.24 | 0.27 | 0.3 | 0.33 | 0.37 | 0.4 | 0.43
Would we be willing to disinvest, and accept performance may worsen slightly – knowing that we are already way ahead of the curve nationally on our performance in this area?
The 3-year DfT Capital Pothole Allocation ceases after the 2024/25 year, and there has so far been no confirmation that this will continue. This is currently worth £13.6m per year
Chart: Capital Carriageway Maintenance Funding and Funding Projections
| 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33
Capital Carriageway Funding (£m) | 66 | 66 | 50 | 36.75 | 40.75 | 40.725 | 40.75
Capital Carriageway Funding - Indicative Projections (£m) | 40.75 | 35.15 | 35.15 | 21.55 | 21.55 | 21.55 | 21.55 | 21.55 | 21.55 | 21.55 | 21.55
Notes: Q. Would we be willing to disinvest, and accept performance may worsen slightly – knowing that we are already way ahead of the curve nationally on our performance in this area?
Include figure from previous slide (35m) in 2023/24
21.55 y 25-onwards

## Slide 25
Chart: Highways Related Claims Received
| 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
Count of Incident Year | 637 | 1430 | 821 | 894 | 1007 | 1101 | 1337 | 1630 | 1741 | 2271 | 2965 | 2582 | 2576 | 3301 | 3094 | 1677 | 1581 | 1348 | 2033 | 1379 | 1618 | 1848 | 1813 | 2369
Spotlight: Highways
Other factors
It’s important to consider the relationship between our road maintenance conditions and road safety and understand what factors can influence road traffic incidents and the impact.
Road traffic accidents can occur for several reasons including weather conditions; traffic congestion; road users; road conditions and more.
Below, the chart shows the number of highways related insurance claims received each year, these include personal injury claims and damages, as the chart show these are increasing.
Serious injuries: 769
Deaths: 49
2022
Vision Zero is our ambition to eliminate deaths and serious injuries on Essex roads by 2040.
Other factors to consider
Insurance claims, open cases:
2019: 41
2020: 73
2021: 65
2022: 132
2023: 852
Notes: Road users: Cars, motorbikes, pedestrians, bicycles
https://saferessexroads.org/visionzero/#:~:text=Whilst%20considerable%20success%20has%20been,recorded%20in%20Essex%20during%202022.

## Slide 26
Performance Reporting Update: The purpose of this update
To provide an overview of the work that has been undertaken regarding performance reporting.
Discuss CLT’s preferred approach to embedding the IMPOWER findings in its own ways of working
Note ongoing work to update strategic measures and rationales. (Change Control)
Discuss and agree approaches to ambition targets, and alignment with transformation.
Highlight interdependencies with other programmes.
Schedule a more substantive update on this work in the new year
Continue engagement on the ambition targets, ‘Just in time’ measures and alignment with transformation.
Supporting KPI workbooks and description of the performance ‘eco-system’ across performance reporting.
New joined up reporting approaches in all functions.
Seeking agreement to:

## Slide 27
CLT to agree corporate targets
Actions taken: small suite of targets included with Q1 reporting
Next steps: ‘stress test’ with finance and engagement with EDs to agree taking these forwards; discussion with PLT;
CLT to define how it works as a performance body
Actions taken: Reports now include clearer direction to issues and proposed actions
Asks of CLT: continue to focus on the presenting issues, and the required function and organisational action
Asks of CLT: agree to engage on the content and processes for embedding these measures; agree how these will be reflected in WCT.
Next steps: consider ‘just in time’ measures that represent immediate operational pressures alongside strategic progress. Review EE measures to progress any change control needed to ensure that strategic measures align with functional delivery
Define role of PBI and other business partners
Take practical steps to join up different performance reporting streams
Actions taken: introduced pre-meets with chairs in ASC to review performance reporting from across the organisation
Next steps: lessons learnt and roll-out to other functions; integration into business planning
Future steps: review BP profiles, and other business partners to ensure alignment
Improve the quality of performance reporting and its transparency
Actions taken: joint sessions with BPs in ASC and Corporate services;
Next steps: roll-out in other functions; ‘just in time’ measures to align with finance reporting timescales
Asks of CLT: agree ‘just in time’ measures.
Actions taken: content for functional and strategic reports continues to evolve
Next steps: publish accessible ‘KPI workbooks’ bringing definitions, rationale and responsibilities
Future steps: map the reporting ‘ecosystem’ of where KPIs and other core measures are reported and shared; roll out KPI workbooks to other reports
Performance Reporting Update:
Recommendations, actions and asks

## Slide 28
One of the requests as part of the performance reporting was to improve the timeliness of the reporting that is available as part of the cycle. The Everyone’s Essex strategic and contextual measures do not readily align themselves with this approach, but there are a range of measures that sit in functions that will give senior leaders a good view of presenting risk and demand, that are reportable monthly. The proposal is to bring light-touch reporting on a suite of measures that provide a view of operational pressures. This could be reported via CLT or OLT.
Proposed measure | Function lead | Benchmark
People waiting for assessments, reviews and DoLS decisions | ASC | Month
Total people admitted to residential care | ASC | Month (comparable rates available)
ASC requests for support | ASC | Month (comparable rates available)
Coroner’s waiting list | CEC | Month
Complaints | CEC | Month
Number of complaints received relating to highways | CEC | Same period the previous year
EHCPs received | CFE | Month (comparable rates available)
Children in care | CFE | Month (comparable rates available)
Total children known to Social Care | CFE | Month (comparable rates available)
EIRs and FOIs responded to in time | Corporate | Month (no national benchmark)
Council tax collection | Corporate | Same period the previous year (comparable rates available)
Unemployment | EIPH | Month (no national benchmark)
Proportion of staff completed all statutory training | P&T | Month
Vacancy rate | P&T | Month (comparable rates available)
Sickness absence | P&T | Month (comparable rates available)
Performance Reporting Update:
‘Just in time’ indicators

## Slide 29
Q3 2023/24
Strategic Indicators: Achievements
properties benefiting from reduced surface water flood risk
215
47% people achieving their health weight outcomes
The Everyone’s Essex Story
Q1 2023/24
Quarter 2 progress 2023/24
Successful Family Solutions an increase on Q4 (77.5%) to 79.7% for Q1 2023-24
3–4-year-old Childcare Funding; Essex is ranked third highest against statistical neighbours at 95.2%
12,760
NHS Health Checks delivered in Q1 2023-24; this is above the target uptake of 12,000.
7.9%
of adults known to secondary mental health services in paid employment
1,117 jobs directly created by ECC programmes
Replacement LED streetlight work continues, saving 6,500 tonnes of carbon per year
532,398 miles have been driven with low or zero emission vehicles, which equates to 66% progress towards committed units.
100,243 miles have been saved due to cycle to work programmes, public transport and carpooling programmes.
The Sustainable Housing Decarbonisation Fund) has now retrofitted 253 homes to an EPC rating of 'C'
MH services & paid employment: ECC already outperforms the national average based on the ASCOF measure and the work to improve recording will mean the significant outperformance
Social Value: 1,425 FTE jobs created, The largest numbers coming from Employment or retention from Local people and NEET.
Notes: has been a delivery of 1,425 FTE jobs. This is 78% progress towards committed units. The largest numbers coming from Employment or retention from Local people and NEET.

## Slide 30: Strategic Indicators: Measures to watch for Quarter 2
Off Target, Out of Range, and Worsening
Off Target but Stable or Improving

## Slide 31: Performance Annex: Quarter 2 performance data

## Slide 32: Strong, Inclusive & Sustainable Economy
Measures reported annually are included on rotation where there are updated figures.
Measure | RAG | Value | Target
Number of people benefitting from ECC skills and employability programmes | È | 1,078 | 6,825 (academic year)
Jobs created directly through ECC programmes | Ç | 338 | 815
Skills, employability and jobs: ​ ​
This is a new target of 6,825 for this academic year (23/34). The current value of 1,078 is for September only due to this being the start of the academic year. It is important to note due to the type of courses on offer these do not all start in September and are spread out throughout the year. These include Multiply, Apprenticeships and entry level up to Level 5 qualifications.​
​
Jobs created directly: ​
​
Jobs directly created through ECC programmes has increased by 40 jobs to 338 (Apr 23-Sept 23). This includes:​ ​
216 entry level jobs in ECC​
122 jobs created and safeguarded by the Business Support contract​

## Slide 33: High Quality Environment
Streetlights: 2023/24 sees the third and final year of Phase 4 of the LED Replacement Programme. This final year should see ECC finalise converting all of our remaining old-style street lighting stock from lamps into LED’s. Last year the upgrade programme was significantly impacted by the global shortage of components for the telecells that are used to control the streetlights. While we were able to recover a lot of lost ground in the final quarter of 22/23, this leaves the final year with a stretching target of 32,476 replacements. It should be noted that this is over 10% larger than the programmes delivered in Year 1 and Year 2 (27,131 and 28,439 replacements respectively).
Measures reported annually are included on rotation where there are updated figures.
Measure | RAG | Value | Target
Retrofit in low-income households | Ç | 253 | 547
Replacing streetlights (mainly residential roads) in Essex with new LED lights | Ç | 16,509 | 32,476
Sections of coastal paths completed | Ç | 0 | 5
Number of properties where risk has been reduced as a result of Flood Management Schemes |  | 0 | 215
Retrofit in low-income households: The SHDF (Sustainable Housing Decarbonisation Fund) has now retrofitted 253 homes to an EPC rating of 'C'. This is 46% towards the target of 547 (with a new deadline of 31 Dec 23). The Home Upgrade Grant Phase 2 (HUG2) Programme budgets have unfortunately been significantly reduced at the request of the government.
Coastal Paths: We are still waiting for approval from the Secretary of State for the two 'part approved' stretches (Harwich to Shotley Gate and Wallasea Island to Burnham). Furthermore, Natural England are still to finalise their report for Mersea Island in order that it can be submitted to the Secretary of State for approval.
Funding has now been secured for the open stretches for last year's maintenance, and costs have been reimbursed for the initial work. We are currently waiting to hear about our application for this year's maintenance on those stretches.
Whilst approval has been granted for the route north of Salcott, the path itself is being revisited to ensure that all the local arrangements are intact.
Flood Management: There are 8 Priority Projects scheduled for 2023/24, providing a reduced surface water flood risk to at least 215 properties. Four schemes are already in construction, and all eight are expected to be achieved by Mar 24. The estimated cost of delivery exceeds the capital programme budget of £4m. The difference will need to be made up of external grants or efficiency savings. In this reporting period £441,500 has been received in grant funding.

## Slide 34: High Quality Environment
CDP Rating: Essex has been rated as one of the best places in the world when it comes to tackling global warming.​
Top marks have been given to Essex County Council for its work on climate action by being awarded an ‘A-Rating’ by CDP, formerly known as the Carbon Disclosure Project.​
The environmental impact organisation, CDP, has recognised Essex as one of only 122 locations across the globe taking bold leadership on environmental action and transparency, despite the pressures of a challenging global economic situation.​
One of 19 UK local authority areas, Essex is the only county council in the UK to be awarded an A rating this year.
Measures reported annually are included on rotation where there are updated figures.
Measure | RAG | Value | Target
ECC rating for CDP ( Carbon Disclosure Project) |  | A | B
Number of trees planted from Essex Forest Initiative |  | 0 | 100,000
Trees: In 2022/23, the target of 75,000 trees was significantly exceeded, with an estimated total of 100,600 trees being planted throughout Essex. The target of 100,000 (40 hectares) in 2023/24 is expected to be achieved; however, the planting season does not start until November, so the progress indicators will show 0 for the early part of the Financial Year. These plantings contribute to achieving our targets for Natural Infrastructure
External funding has been secured, as follows:
Up to £2.1m over 3 years from the Urban Tree Challenge Fund (Forestry Commission)
Up to £300k over 3 years from the Local Authority Treescape Fund (Forestry Commission) to support four landowners with their England Woodland Creation Offer applications.
Up to £32k from the Tree Production Capital Grant Forestry Commission) for the creation of 2 community tree nurseries.
£381k from National Highways' Designated Funds for 30 years of improved woodland management across the unstaffed woodland estate.
In addition, we are waiting to hear back from a collaborative bid for the Coronation Living Heritage Fund for the planting of up to nine new orchards.

## Slide 35: Health, Wellbeing & Independence for all Ages 2
Measure | RAG | Value | Target
Number of adult social care users in receipt of care technology | Ç | 8,049 | 4,195
% of adults with a learning disability that transition into adult social care in residential care | È | 7.7% | N/A
Percentage of adults known to secondary mental health services in paid employment | Ç | 8.2% | 7.0%
Care technology: There are a total of 8,049 service users in the service at end of Sept 23. New installs since July 2022 is 5,350. Care Technology is delivering avoidable savings of ~£573,000 against the 2023/24 MTRS target. The monitoring and response service has attended 3,299 response visits and picked up 1,559 fallers since go live which has saved an additional £1,626,600 avoidable NHS costs due to ambulance call outs and days in hospital.
We’ve trained 1,626 internal and external individuals to prescribe care technology across Essex, 33% external.
Across the contract, we’ve seen ~£10.36M return in Social Value across employment, training, green project and reducing public service demand.
Mental Health services & paid employment: Further work is underway by EPUT to improve the recording in this area. ECC already outperforms the national average based on the ASCOF measure and the work to improve recording will mean the significant outperformance which ECC achieves in this area will be fully reflected for the 23/24 national reporting.
LD
LD Trans to Res: 13 adults with Learning Disabilities transitioned across to Adult Social Care during the last quarter. 1 of those adults was in residential care at the point they were transitioned into adult social care.

## Slide 36: Health, Wellbeing & Independence for all Ages 2
Measure | RAG | Value | Target
The proportion of adults in contact with secondary mental health services (services generally requiring referral by a GP) living independently, with or without support | È | 17.7% | 15.8%
Percentage of adults who are self-caring post reablement on discharge from hospital | Ç | Q1 value: 50.9% Q2: TBC* | 52%
Number of total population aged 40-74 receiving an NHS Health Check | Ç | 26,066 | 48,000
NHS Health Check: Q2 saw 13,212 health checks completed for those eligible in Essex, this is 110% of the target needed for this quarter and is higher than the 12,854 completed within Q1. In terms of YTD, we have completed 26,066 health checks against a target of 24,000 – this represents delivery of nearly 109% so far this year. In terms of health checks offered the cumulative total is 61,476 against our target in the YTD.
*Q2 data for ‘Reablement’ is to be confirmed once the data is validated.
Mental Health: Data validation exercise underway at EPUT which includes some changes to their case management system and additional training for staff. Preview of October data suggests they are starting to see genuine improvements from this work.

## Slide 37: A Good Place for Children and Families to Grow 1
Measure | RAG | Value | Target
Percentage of families with successful intervention (Family Solutions) | Ç | 84.9 | 85%
Family Solution interventions: The Volume of successful intervention for Family Solutions between July 1st 2023 and September 30th 2023 is 84.9% this is 7.9% points above the previous quarters 79.7% successful interventions.
Family Solutions closed 440 families in the last quarter, 212 of these cases were closed after an extended intervention, the remaining cases were closed as ‘Decision not to proceed’ or ‘Family Solutions not required’.

## Slide 38: A Good Place for Children and Families to Grow 2
Measure | RAG | Value | Target
The number of children known to social care per 10,000 | È | 183.3 | 190 – 210 (Target range)
The number of children subject to Children in Need plans per 10,000 | Ç | 49.1 | 47.3 - 63.1 (Target range)
The number of children subject to child protection plans per 10,000 | Ç | 24.6 | 17.3 - 20.5 (Target range)
Children known to social Care:
The number of children open to social care has decreased from 191.7 per 10,000 to 183.29 in September 2023, similar to rates seen in 2022.
During the last 2 years North has consistently had the greatest number of children open to social care and the highest rate per 10,000. Due to the number of SMC in West, they have seen an increase in the number of children open to social care from 1329 (152.7 per 10,000) in September 2021 to a peak of 1600 (183.9 per 10,000) in June 2023. In September 2023, although North and West have a similar number of children open to social care (1532 and 1530 respectively), North has the highest rate per 10,000 of all the quadrants at 225.26, but West has seen a dip in their rate and has the least at 150.68 per 10,000.
We have also included the numbers of children open to social care for additional context.
Children in Need (CIN) and Child Protection plans:
The number of children on child in need plans in Essex has fluctuated over the last 12 months, reaching a peak of 1661 in March 2023, falling to 1556 in September, in line with levels seen last October. The main cause for this is the number of mainstream CIN volumes dropping to their lowest number of 812 in September, with CWD and Case Managed plans remaining relatively stable.
The rate of children in need has increased from 46.2 and 46.4 per 10,000 in 2022, to rates between 48.7 and 50.1 in 2023, although higher are still in the expected range. North continues to have the highest rate per 10,000 and has seen an increase to 62.2 in September, significantly higher than the other quadrants, whose rates are between 43.4 and 48.9.
Child Protection Plans: The number of children subject to Child Protection plans was relatively stable during Q4 of last year, with numbers between 680 and 690. However, numbers have risen since March 2023, reaching 733 in June. This measure is rated as red as the rate of children on child protection plans continues to be slightly above the threshold range, however as noted previously – Essex continues to have a lower proportions of children on child protection plans than similar authorities.
At a quadrant level, the rate per 10,000 varies significantly, with notably more children on a child protection plan in North than the other three quadrants. Rates have risen from 32.8 to 36.6, while the other quadrants generally see rates between 15 and 22.

## Slide 39: A Good Place for Children and Families to Grow 2
Measure | RAG | Value | Target
Number of looked after children per 10,000 | È | 36.5 | 34.7 - 39.4 (Target range)
Review representation of Ethnically Diverse CYP across the statutory social care system: Open to social care | Ç | 23.3% | N/A
Review representation of Ethnically Diverse CYP across the statutory social care system: Children in Care | Ç | 26.9% | N/A
Review representation of Ethnically Diverse CYP across the statutory social care system: Child protection | Ç | 14.3% | N/A
Looked After Children: The number of children in care rose during 2022 and continues to see higher numbers. Following a peak in November, volumes have been more consistent, fluctuating between 1150 and 1170, currently sitting at 1160 in June. Despite the increases that have been seen over time, the number of children looked after by the council remains in our expected range.
At a quadrant level, North continues to see significantly higher rates of children in care per 10,000 but has seen rates fall from 50.6 in June 2022 to 46.6 by June 2023. West has also seen rates rise, heavily impacted by the rising number of SMC during qu4 of 2022/23.
Children from an ethnically diverse group: The proportion of children open to social care from an ethnically diverse group has grown gradually over time, and currently sits at 23.2%, slightly more than last quarter (21.9%).
The increase is mainly reflected in the children in care numbers, where a higher number of separated migrant children is seen; 68.5% of SMC in care being of other ethnic groups for example. The proportion of children in care from Global Majority backgrounds falls from 26.2% to 15.6% when SMC are excluded, which is much closer to the Essex school census rate of 14.3%.

## Slide 40: Service Excellence
Measures reported annually are included on rotation where there are updated figures.
Council Tax collection: The 2023/24 Q2 forecast for the in-year collection rate is 96.6%, which is 0.5% less than reported at Q1.
Currently, districts are forecasting over £14.5m of council tax income collection this financial year relating to prior years, which is the equivalent of about a 1.5% increase in the collection rate.
So, if we apply this on top of the current 96.6% average collection rate that we have in-year, the overall collection of council tax remains on target and on budget, which is why the billing authorities are forecasting a collection fund surplus, which ECC will benefit from in 2024/25.
Social Value: Within the theme of ‘A Strong Inclusive Sustainable Economy’ there has been a delivery of 1,425 FTE jobs. This is 78% progress towards committed units. The largest numbers coming from Employment or retention from Local people and NEET.
There has been a total of 106 tonnes of CO2 emission savings which equates to 50% progress on delivery of units committed, from either renewable energy measures or Savings in CO2e emissions on contract achieved through de-carbonisation.
A total of 100,243 miles have been saved due to cycle to work programmes, public transport and carpooling programmes.
A total of 532,398 miles have been driven with low or zero emission vehicles, which equates to 66% progress towards committed units.
The overall committed value toward the strategic aim of Health Wellbeing and independence of people in Essex has 42% progress towards the committed value. This is inclusive of £468,616 worth of initiatives taken & staff time invested with £148,517 focussed on mental health for adults & children initiatives.
Measure | RAG | Value | Target
Collection rate of Council Tax achieved for the year | È | 96.6% | 98%
Deliver social value through procurement and practice SV % Delivered SV Committed (£) SV Delivered (£) |  | 38.0% £97,510,914 £36,931,323 | N/A

## Slide 41: OFLOG measures
2021/22 performance data

## Slide 42
Household waste recycling rate (%) | Essex 49.70 (can be broken down further for districts) Mean for all English county local authorities: 46.81
Residual household waste (kg per household) | Essex: 534.70kg can be broken down further for Essex districts/authorities
Recycling contamination rate (%) (estimated rejects) | Essex: 4.13 Mean for all English county local authorities: 6.14
Requests resulting in a service | Essex: 1,310 per 100,000 population Median of Essex’s CIPFA Nearest Neighbours: 1,512 per 100,000 England Median: 1,708 per 100,00 population
Workforce turnover rate | Essex: 30% Median of Essex’s CIPFA Nearest Neighbours: 30.8% England Median: 28.9%
People in adult social care, quality of life | Essex: 0.427 (value range -0.8 to 1.0) Median of Essex’s CIPFA Nearest Neighbours: 0.410 England Median: 0.409
Carers of people in adult social care, quality of life | Essex: 7.6 (value range 0 to 12) Median of Essex’s CIPFA Nearest Neighbours: 7.1 England Median: 7.2
Short-term service provision | Essex: 71.5% Median of Essex’s CIPFA Nearest Neighbours: 84.8% England Median: 76.4%
People who use services who found it east to find information | Essex: 63.1% Median of Essex’s CIPFA Nearest Neighbours: 63.2% England Median: 65.2%
Carers who found it easy to find information about services | Essex: 58.0% Median of Essex’s CIPFA Nearest Neighbours: 60.9% England Median: 57.3%
Oflog Measure
Latest data available (2021/22)
OFLOG Measures

## Slide 43
Oflog Measure
Latest data available (2021/22)
19+ further education and skills achievements per 100,000 population | Essex: 2,371 Mean for all English Counties: 2,620
19+ further education and skills achievements per 100,000 population (excluding apprenticeships) | Essex: 1,984 Mean for all English Counties: 2,196
Adults with a Level 3 or above qualification | Essex: 53.5% ​ Median for English Counties: 60.3%
Non-ringfenced reserves as % of net revenue expenditure | Essex: 61.7% ​ Median for Essex’s CIPFA nearest neighbours: 50.0%​ Median for English Counties: 47.3%​
Non-ringfenced reserves as % of service spend | Essex: 50.3% ​ Median for Essex CIPFA nearest neighbours: 40.8%​ Median for English Counties: 40.5%​
Total core spending power per dwelling (£) | Essex: £1,535.55 Median for Essex CIPFA nearest neighbours: 1,530.68​ Median for English Counties: £1,542.55
Level of Band D council tax rates (£) (excluding parishes) | Essex: £1,340.91 Median for Essex CIPFA nearest neighbours: £1,410.00​ Median for English Counties: £1,414.91
Social care spend as % of core spending power | Essex: 73.1%​ Median for Essex CIPFA nearest neighbours: 73.8%​ Median for English Counties: 72.0%
Debt servicing as % of core spending power | Essex: 5.2%​ Median for Essex CIPFA nearest neighbours: 6.5%​ Median for English Counties: 6.3%
Total debt as % of core spending power | Essex: 101.9%​ Median for Essex CIPFA nearest neighbours: 99.1%​ Median for English Counties: 103.0%​
OFLOG Measures

## Slide 44: This information is issued by: Essex County Council
Contact the team directly:
Duncan.Taylor@essex.gov.uk; Louisa.Thomas@essex.gov.uk;
Performance & Business Intelligence, Corporate Team Essex County Council County Hall, Chelmsford Essex, CM1 1QH
facebook.com/essexcountycouncil
Essex_CC
The information contained in this document can be translated, and/or made available in alternative formats, on request.
Published October 2023